## Induction Plan - Development (hidden)
SN | Activity Description | Responsibility | Estimated Effort | Schedule | Planned Start Date | Planned End Date | Actual Start Date | Actual End Date | Status
1 | Overview of IOP and IOP Publishing at account level | PM/BA | 2 hours | Day 1
2 | Overview of IOPP project specific functionality | BA | 2 hours | Day 1
3 | System, environment and projects setup
| IOPscience | Self | 4 hours | Day 1
| Alerts | Self | 4 hours | Day 2
| Uploaderator and Synchronizer | Self | 4 hours | Day 2
4 | Technology
| Spring MVC | Self | 16 hours | Day 3, 4
| JQuery | Self | 8 hours | Day 5
| JPA | Self | 16 hours | Day 6, 7
| Groovy / Grails | Self | 16 hours | Day 15, 16
| Alfresco | Self | 8 hours | Day 17
| MarkLogic | Self | 8 hours | Day 18
5 | Technical architecture walkthrough | TL | 2 hours | Day 8
6 | GIT overview | Dev | 2 hours | Day 8
7 | Explore GIT in detail | Self | 4 hours | Day 8
8 | Domain driven design overview | TL | 2 hours | Day 9
9 | Reading on domain driven design | Self | 6 hours | Day 9
10 | High level walkthrough of the IOPscience platform, code, reusable components | TL | 3 hours | Day 10
11 | Explore and understand JIRA / Confluence | Self / Dev | 5 hours | Day 10
12 | Explore and understand IOPscience platform and code | Self | 3 hours | Day 11
13 | Explore and understand continuous integration | Self / Dev | 5 hours | Day11
14 | Resolve backlog item(s)
| Analysis | Self | 8 hours | Day 12
| Development | Self | 16 hours | Day 13, 14

## Doc Info
Induction Plan - Security Testing
Project |  | --
Customer |  | --
Author |  | Sandeep H. Maher
Version |  | 0.1
Date |  | 2019-04-08
Status |  | Draft
Document History
Version | Date | Description | Author | Reviewer
0.1 | 2019-04-08 | First draft | Shailendra, Sandeep H. Maher | --
--

## Induction Plan - Testing (hidden)
Induction Plan for Ajaikumar Nadar
# | Activity Description | Responsibility | Estimated Effort | Schedule | Planned Start Date | Planned End Date | Actual Start Date | Actual End Date | Status
1 | Showing him around and introductions within BA/Test team with seniors (Leads, Managers,..) | Akshatha | -- |  | 2019-04-01 | 2019-04-01 | 2019-04-01 | 2019-04-01 | Complete
2 | Ensuring Access Rights to new joinee to filesystem area via ITS support | Shailendra | -- |  | 2019-04-01 | 2019-04-01 | 2019-04-01 | 2019-04-01 | Complete
3 | Ensuring update of Test&BA Team Profile-Arrk.xlsx | Shailendra |  |  | 2019-04-01 | 2019-04-01 | 2019-04-02 | 2019-04-02 | Complete
4 | Inclusion in Distribution lists: - TestingBA.team group id - Testing.team group id | Shailendra | -- |  | 2019-04-01 | 2019-04-01 | 2019-04-01 | 2019-04-01 | Complete
5 | Access to Whizible | Shailendra | -- |  | 2019-04-02 | 2019-04-02
6 | Overview of Testing @ Arrk | Shailendra |  |  | 2019-04-02 | 2019-04-02 | 2019-04-02 | 2019-04-02 | Complete
8 | Overview of Security Testing @Arrk | Akshatha |  |  | 2019-04-04 | 2019-04-08
- Introduction to Security Testing focus group
| - Current Capabilities | [7 empty] | --
| - Goal and plan for 2019 | [7 empty] | --
- Security Testing Checklist
9 | Go Through the Securty Test Checklist | Ajai |  |  | 2019-04-01 | 2019-04-05
- Self study , review and enhancements
- Checklist Update
- Present revised checklist
10 | Introduction to Security Testing Lab | Akshatha |  |  | 2019-04-09 | 2019-04-09
- Taking control (credentials, Access, softwares etc)
11 | Getting acquainted with Security Testing Lab |  |  |  | 2019-04-09 | 2019-04-12
| -Understand installed softwares | Ajai
| -Additional software needed, installation etc. | Ajai, Akshatha
12 | Introduction to SDLC and STLC | Shailendra |  |  | 2019-04-09 | 2019-04-09
-Types of Testing (what/when/how)
-Non functional testing
13 | Penetration testing training | Arrk |  |  | TBD
14 | Security Testing for project
| -Brookson LOCUM overview | Anup
| -Brookson LOCUM testing plan | Juni, Ajai, Akshatha
| -Brookson LOCUM testing | Ajai
15 | Gaining tools expertise | Ajai
| -Zed Attack proxy (study, implement, debrief) |  |  |  | April
| -Burp Suite |  |  |  | May
| <tool> |  |  |  | June
| <tool> |  |  |  | July
16 | OWASP Top Ten Threats and Tools | Ajai |  |  | Ongoing
-SQL Injection (Study, implement, debrief)
-XSS
-CSRF
-Man in the Middle
17 | OWASP Mobile Security | Ajai |  |  | Ongoing
-Concepts
-Tools
18 | Training to Team | Ajai |  |  | Ongoing
-Presenting learning to team
-Tool demonstration
19 | Observe TOTUM penetration testing | Ajai |  |  | TBD
-Learn through observation
-Tools and techniques used

## Key Outcomes
Particulars |  | Status | Remarks
April 2019
Achieved clear understanding of role and objectives
Basic induction completed
Understanding of Manual Testing, SDLC
Acquired control of Security Lab along with software installed etc.
Indepth study - SQL Injection attacks, SQLmap
Indepth study - ZAP tool
Project testing - Brookson
May 2019
Presentation of SQL Injection attacks to testers
Understanding of testing types
Contribute to manual testing <Project>
Indepth study - XSS, related tools
Indepth study - ZAP tool
Project testing - <TBD>
June 2019
Successfully completed Python course
Understanding of Automated testing
Presentation of XSS to testers
Indepth study - CSRF, related tools
Indepth study - Unix shell scripting
Indepth study - Burp suite, Nmap
Project testing - IFC
Observe Pen testers at work-TOTUM?
July 2019
Presentation of CSRF to testers
Understanding of Performance testing
Indepth study - Networking, related tools
Indepth study - Mobile apps Security, tools
Indepth study - Security testing Browser add-ons
Project testing - <TBD>
Participate in Pen Testing training?
August 2019
Presentation of Browser add-ons to testers
Indepth study - OWASP standards
Indepth study - Acunetix
Project testing - <TBD>
September 2019
Successfully completed Perl course
Present Security testing framework
Indepth study - Cryptography
Indepth study - Path Traversal
Project testing - <TBD>

## Reading references
Date | Reference | Particulars
2019-04-08 | WebURL | Which are best ethical hacking and pentesting books for beginners?
The list below is recommended reading for all testers to scale their security testing knowledge.
Thanks, Ajaikumar Nadar

## Books, Training needs
Date | Reference | Particulars | Status

## Security Assets
LIST OF SECURITY TESTING ASSETS CREATED
Date | Asset | Details